## Project
Matrix A Transit System
| Team Members | NUID
1 | Mohammed Omer Qasim Shaik | 2707760
2 | Rekha Samrajyutha Sajja | 2655060
3 | Sai Sindhu Thondapu | 2785016
4 | Shaiz Akhtar Mohammad | 2796856
5 | Srinivasa Reddy Akumalla | 2798166

## User Stories
User Story Num | User Story | Description | Start Date | End Date
Matrix_01 | Project Requirements | Discussion on various requirements of the project | 21/11/2022 | 25/11/2022
Matrix_02 | Business Rules | Design business rules in detail | 26/11/2022 | 28/11/2022
Matrix_03 | Final ERD | Design final ERD as per the changes requested by the customer and explain it | 30/11/2022 | 2022-01-12
Matrix_04 | Designing of tables | Design the tables as per the final ERD which includes all changes and new requirements given by the customer | 2022-02-12 | 2022-05-12
Matrix_05 | Implementation of tables | Implement the designed tables | 2022-02-12 | 2022-05-12
Matrix_06 | Report | Prepare the final document which includes all the ER diagrams, business rules, application changes and new functionalities | 2022-06-12 | 2022-10-12
Matrix_07 | PPT | Prepare final PPT for the presentation | 2022-07-12 | 2022-11-12

## Omer
User story | Tasks | To Do | Inprogress | Completed | Blocked | Issue Description | Task Assigned to | Start Date | End Date | Deadline
Matrix_02 | Business rules | [5 empty] | Omer | 26/11/2022 | 28/11/2022 | 28/11/2022
Matrix_03 | Final ERD | [5 empty] | Omer | 30/11/2022 | 2022-01-12 | 2022-01-12
Matrix_04 | Design below data tables 1. Employee 2. Payroll 3. Insurance 4. Department | [5 empty] | Omer | 2022-02-12 | 2022-03-12 | 2022-05-12
Matrix_05 | Implement below data tables 1. Employee 2. Payroll 3. Insurance 4. Department | [5 empty] | Omer | 2022-03-12 | 2022-05-12 | 2022-05-12
Matrix_06 | Report 1. ERD 2. Entities 3. Views scenario 1 | [5 empty] | Omer | 2022-06-12 | 2022-10-12 | 2022-10-12
Matrix_07 | Work on the below slides 1. ERD 2. Busines rules | [5 empty] | Omer | 2022-08-12 | 2022-10-12 | 2022-11-12

## Rekha
User story | Tasks | To Do | Inprogress | Completed | Blocked | Issue Description | Task Assigned to | Start Date | End Date | Deadline
Matrix_02 | Business rules | [5 empty] | Rekha | 26/11/2022 | 28/11/2022 | 28/11/2022
Matrix_03 | Final ERD | [5 empty] | Rekha | 30/11/2022 | 2022-01-12 | 2022-01-12
Matrix_04 | Design below data tables 1. Vehicle 2. Maintenance 3. Vendor 4. Route | [5 empty] | Rekha | 2022-02-12 | 2022-05-12 | 2022-05-12
Matrix_05 | Implement below data tables 1. Vehicle 2. Maintenance 3. Vendor 4. Route | [5 empty] | Rekha | 2022-02-12 | 2022-05-12 | 2022-05-12
Matrix_06 | Report 1. Reasons for successful project 2. Views scenario 3 | [5 empty] | Rekha | 2022-06-12 | 2022-09-12 | 2022-10-12
Matrix_07 | Work on the below slides 1. Approach slide 1 2. Approach slide 2 | [5 empty] | Rekha | 2022-08-12 | 2022-11-12 | 2022-11-12

## Shaiz
User story | Tasks | To Do | Inprogress | Completed | Blocked | Issue Description | Task Assigned to | Start Date | End Date | Deadline
Matrix_02 | Business rules | [5 empty] | Shaiz | 26/11/2022 | 28/11/2022 | 28/11/2022
Matrix_03 | Final ERD | [5 empty] | Shaiz | 30/11/2022 | 2022-01-12 | 2022-01-12
Matrix_04 | Design below data tables 1. Ride History 2. Fare Enum 3. Helpdesk | [5 empty] | Shaiz | 2022-02-12 | 2022-04-12 | 2022-05-12
Matrix_05 | Implement below data tables 1. Ride History 2. Fare Enum 3. Helpdesk | [5 empty] | Shaiz | 2022-03-12 | 2022-05-12 | 2022-05-12
Matrix_06 | Report 1. Business Rules 2. Views scenario 2 | [5 empty] | Shaiz | 2022-07-12 | 2022-10-12 | 2022-10-12
Matrix_07 | Work on the below slides 1. Concepts slide 1 2. Concepts slide 2 | [5 empty] | Shaiz | 2022-07-12 | 2022-10-12 | 2022-11-12

## Sindhu
User story | Tasks | To Do | Inprogress | Completed | Blocked | Issue Description | Task Assigned to | Start Date | End Date | Deadline
Matrix_02 | Business rules | [5 empty] | Sindhu | 26/11/2022 | 28/11/2022 | 28/11/2022
Matrix_03 | Final ERD | [5 empty] | Sindhu | 30/11/2022 | 2022-01-12 | 2022-01-12
Matrix_04 | Design below data tables 1. Customer 2. Card 3. Transaction History | [5 empty] | Sindhu | 2022-02-12 | 2022-05-12 | 2022-05-12
Matrix_05 | Implement below data tables 1. Customer 2. Card 3. Transaction History | [5 empty] | Sindhu | 2022-03-12 | 2022-05-12 | 2022-05-12
Matrix_06 | Report 1. Project Tracking 2. Views scenario 4 | [5 empty] | Sindhu | 2022-06-12 | 2022-10-12 | 2022-10-12
Matrix_07 | Work on the below slides 1. Overview 2. Benefits 3. Project Management | [5 empty] | Sindhu | 2022-07-12 | 2022-10-12 | 2022-11-12

## Srinivas
User story | Tasks | To Do | Inprogress | Completed | Blocked | Issue Description | Task Assigned to | Start Date | End Date | Deadline
Matrix_02 | Business rules | [5 empty] | Srinivas | 26/11/2022 | 28/11/2022 | 28/11/2022
Matrix_03 | Final ERD | [5 empty] | Srinivas | 30/11/2022 | 2022-01-12 | 2022-01-12
Matrix_04 | Design below data tables 1. Cust Account 2. Vehicle Schedule 3. Employee Schedule | [5 empty] | Srinivas | 2022-02-12 | 2022-02-12 | 2022-05-12
Matrix_05 | Implement below data tables 1. Cust Account 2. Vehicle Schedule 3. Employee Schedule | [5 empty] | Srinivas | 2022-03-12 | 2022-05-12 | 2022-05-12
Matrix_06 | Report 1. About the project 2. Views scenario 4 | [5 empty] | Srinivas | 2022-07-12 | 2022-09-12 | 2022-10-12
Matrix_07 | Work on the below slides 1. Concepts slide 3 2. Concepts slide 4 | [5 empty] | Srinivas | 2022-07-12 | 2022-11-12 | 2022-11-12